## Spreadsheet
Quarterly plan
Q2 2021
Week | ML Microservice | est. Time [days]
2021-03-29 | build system | 3
2021-04-05 | test continuous integration | 3
2021-04-12 | API that returns no data | 4
2021-04-19 | test continuous delivery | 2
2021-04-26 | integrate ML model | 5
2021-05-03 | implement automated testing | 3
2021-05-10 | description on landingpage | 3
2021-05-17 | installation instructions in README | 4
2021-05-24 | README finished | 4
2021-05-31 | Microservice ready for QA | 5
2021-06-07
2021-06-14
Goals
ML API
Load Test
CI/CD
Yearly plan
2021
Quarter | Product | est. Time [weeks]
Q1 2021 | Small Azure WebApp for leanrning | 10
Q2 2021 | Housing prices API | 10
Q3 2021 | Extend API with image recognition of fascades for better accuracy | 11
Q4 2021 | Migrate model to neural network | 11
Goals
Prediction API
Image recognition
neural network